## Slide 1
Release Kickoff
Sanitized work sample for GitHub portfolio
PROGRAM MANAGEMENT
RELEASE READINESS
CROSS-FUNCTIONAL DELIVERY
Purpose
Align teams on scope, schedule, risks, dependencies, and release governance before execution begins.
Modernized from an older release kickoff deck. Names, internal URLs, customer references, and proprietary identifiers have been removed.
Sanitized GitHub work sample • Confidential details removed
1
Notes: Slide 1: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 2
RELEASE KICKOFF
Kickoff Objectives & Agenda
Objectives
Confirm release goals, delivery model, and scope boundaries.
Plan
Review milestones, team deliverables, dependencies, and readiness gates.
Governance
Align on branching, build cadence, decision points, and escalation paths.
Agenda
• Release timeline and readiness gates
• Workstream deliverables and ownership
• Dependencies, risks, and mitigations
• Branching / build management
• Open questions and decisions needed
Sanitization applied
• Specific customer names replaced with segments
• Internal links and aliases removed
• Ticket IDs generalized or omitted
• Old visual styling replaced with clean template
Sanitized GitHub work sample • Confidential details removed
2
Notes: Slide 2: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 3
RELEASE KICKOFF
Release Schedule At A Glance
Code & Merge
Aug–Nov
Feature Test
Nov–Dec
Integration
Dec–Jan
Regression
Jan–Feb
Final Builds
Feb
Staging
Feb–Mar
Beta
Mar–Apr
Production
Apr–May
Planning principle
Use gates to make release health visible early: feature completion, integration stability, regression readiness, staging confidence, and production go/no-go.
Sanitized GitHub work sample • Confidential details removed
3
Notes: Slide 3: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 4
RELEASE KICKOFF
Workstream Overview
Analytics & Data
Central ingestion, data utilities, search terms, scale validation
Network Services
URL filtering, private network routing, profile management
Device Platform
Small-form-factor device support, logging, packaging, configuration
Security & Reliability
Auditability, hardening, resilience, dependency cleanup
Release Engineering
Kernel / package upgrades, branching, builds, smoke-test criteria
Connectivity Innovation
Evaluation of multi-transport connectivity and integration options
Sanitized GitHub work sample • Confidential details removed
4
Notes: Slide 4: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 5
RELEASE KICKOFF
Deliverable Review Format
Workstream
Feature Summary
Implementation
Dependencies
Risks
Analytics
Central ingestion and utility integration
POC → plugin build → scale test
Data platform + network provisioning
Infra availability and scaling assumptions
Network Services
URL filtering and private network support
Policy model + routing profile updates
Security appliance setup
Performance impact and migration gaps
Device Platform
Small device support and virtual controller options
Packaging + config generation
Hardware + license readiness
Memory / footprint constraints
Release Eng.
Kernel, package, and branch readiness
Build cadence + smoke criteria
Cross-branch merge discipline
Unknown code references
Use a consistent template to keep discussions concise and decision-oriented.
Sanitized GitHub work sample • Confidential details removed
5
Notes: Slide 5: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 6
RELEASE KICKOFF
Dependency & Ownership Map
Architecture
Requirements, patterns, design approval
Engineering
Feature delivery and implementation
QA / Release
Testing and readiness evidence
Infrastructure
Environments and provisioning
Program Lead
Cadence, decisions, risks, alignment
Weekly reviews focus on unblocking cross-team work, not re-statusing every task.
Sanitized GitHub work sample • Confidential details removed
6
Notes: Slide 6: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 7
RELEASE KICKOFF
Risk Themes & Mitigations
Risk Theme
Why it matters
Mitigation
Environment readiness
Provisioning, networking, or test data not available when feature teams need it.
Track as gated dependency with named owner and target date.
Unclear scope
Feature boundaries or acceptance criteria not fully decomposed.
Require epics/stories before execution gate.
Performance uncertainty
New architecture or scale assumptions are unproven.
Time-box POC and define pass/fail metrics early.
Cross-branch churn
Prior release changes need merge-forward discipline.
Freeze criteria, merge checklist, and smoke-test evidence.
Sanitized GitHub work sample • Confidential details removed
7
Notes: Slide 7: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 8
RELEASE KICKOFF
Branching & Build Governance
Before release branch
• All release work stays on team / feature branches
• Previous release stories and defects are closed
• Two consecutive successful smoke-tested builds
After release branch
• Merge prior release changes forward
• Merge completed feature work into release branch
• Create installable builds from supported tooling
• Share issues through the agreed escalation path
Feature Branches
Release Branch
Nightly Build
Smoke Test
Distribution
Sanitized GitHub work sample • Confidential details removed
8
Notes: Slide 8: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 9
RELEASE KICKOFF
Decisions Needed
01
Scope
Which deliverables are committed for the release versus candidates?
02
Readiness
What evidence is required to exit each quality gate?
03
Dependency Owners
Who owns environment, appliance, license, data, and provisioning blockers?
04
Escalation
What decisions need leadership attention before execution starts?
Outcome: a shared release plan with clear owners, visible risks, and agreed gate criteria.
Sanitized GitHub work sample • Confidential details removed
9
Notes: Slide 9: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.

## Slide 10
WRAP-UP
Next Steps
Post-kickoff actions
• Publish action log and decision summary
• Confirm owners for dependencies and risks
• Update roadmap / release tracker with agreed scope
• Schedule targeted follow-ups only where needed
GitHub usage notes
• Use as a portfolio-safe example of release orchestration
• Keep company, customer, and internal system names out
• Replace sample dates and workstreams as needed
• Export PDF copy for easier preview in repos
Questions & Discussion
Sanitized GitHub work sample • Confidential details removed
10
Notes: Slide 10: Sanitized portfolio version. Replace sample content with your specific non-confidential work sample details if needed.